## Project Plans
Hunt Highway & Attaway Road Improvements
Town of Florence
Comment Resolution Form
Deliverable: |  | Hunt Highway & Attaway Road Improvements |  |  | Design Consultant: |  | Wilson & Company
Deliverable Date: |  |  | Document(s): | Hunt Highway Intersection Improvements Project (T-91 100% Plans) | Design Phase: |  | 100% NFC Plans
Comments Due Date: |  | 2025-10-28 | Owners Rep: | Lindsey Randall | Disposition Codes: |  | (A) Will Comply (B) Consultant to Evaluate (C) Client to Evaluate (D) No Further Action
Resolution Meeting Date: |  | TBD | Consolidator(s): | Banicki Construction / Trace / Town of Florence | Abbreviations: |  | (No) Comment Number (IDC) Initial Disposition Code (FDC) Final Disposition Code
Reviewer Guidance: |  | 1. Under "REVIEWER", provide first name initial and your full last name.
2. Under "REFERENCE", provide specific comment location. When referencing a drawing use drawing number, sheet number and revision in parentheses, example: "MTC-CV-001 (1, rev 0)"
3. Under "COMMENT DESCRIPTION", provide clear and specific comments; please avoid open ended written conversations.
Designer Guidance: |  | 1. Under "RESPONSE BY", provide first name initial and your full last name.
2. Under "IDC", provide initial disposition that correlates with response.
3. Under "RESPONSE DESCRIPTION / COORDINATED RESPONSE", provide clear and specific response to comments; ensure all items in review comment have been addressed. The phrase "…/COORDINATED RESPONSE" defines the generated (and/or updated) response that has been coordinated with other team members, on or before the comment resolution meeting, in order to determine final disposition.
4. Under "FDC", provide final disposition that correlates with agreed upon response during the comment resolution meeting.
REVIEWER COMMENTS |  |  |  |  | RESPONSE
No | AGENCY / FIRM | REVIEWER | REFERENCE SHEET # | COMMENT DESCRIPTION | RESPONSE BY | IDC | RESPONSE DESCRIPTION / COORDINATED RESPONSE | FDC
1 | JBC | AND | 1 | Can Wilson provide their Utility Contacts contact information? | ERG | A | Utility Contacts information will be shared, but might be out of date due to the project being on hold for 2 years | A
2 | TRACE/TOF | LR | 1 | Update Town information. Mayor - Keith Eaton Vice Mayor - Cathy Adam Town Council: Arthur Neal, Nicole Bucellato, Jose Maldonado, Tony Bencina, Sherrie Bedford. | ERG | A | Town information will be updated | A
3 | TRACE/TOF | LR | 2 | Remove All Plans for construction within Town ROW or easements shall have the following notes. | ERG | A | Will be removed | A
4 | TRACE/TOF | LR | 2 | General Note #1: Could this information be added to the specs for the project? | ASF | D | This note is to cover standard details and associated specificatoins. The project specifications will have special provisions for items that do not fall under a standard spec or if it is modified. It will be referenced in specs as well. | D
5 | TRACE/TOF | LR | 2 | General Note #1: Some improvements adhere to ADOT specs (guardrail, signals, striping, signing, others). Need to add reference to ADOT specs. | ASF | A | Will modify note #1 to include ADOT specs | A
6 | JBC | AND | 2 | General Note #3 - Are there specific permits that should be addressed here that the Town will be responsible for? | ASF | B/C | Town's general note to remain. Revised for clarification | D
7 | JBC | AND | 2 | General Notes #5 - If subcontractors are working under the prime contractor, do the subcontractors still need their own BL? | ASF | B/C | The Town's general note. Clarify with Town that it is not required per current CMAR contract. | D
8 | JBC | AND | 2 | General Note # 12 - Is there something specific that will need to be removed that isn't addressed in the Summary of Quantities? | ERG | B | note was removed for clarification. Removals were noted in plans | A
9 | TRACE/TOF | LR | 2 | GCN #20: Remove note. | ERG | A | Note was removed. | A
10 | TRACE/TOF | LR | 2 | GCN #32: Remove "within a new subdivision" | ERG | A | Removed "within a new subdivision' from note | A
11 | TRACE/TOF | LR | 2 | Engineers Notes #3: Add "unless otherwise directed by the utility owner". | ERG | A | Added "unless otherwise directed by the utility owner" | A
12 | TRACE/TOF | LR | 2 | Grading & Drainage Construction Notes: Remove "Plans for grading and drainage construction shall have the following notes shown on the cover, note or detail". | ERG | A | To be removed | A
13 | TRACE/TOF | LR | 2 | Grading & Contruction Notes: most of these notes are not applicable to this project. | ERG | B | Will evaluate which notes are required. Removing notes | A
14 | TRACE/TOF | LR | 3 | If (155) is within new pavement limits, need to reset to finished grade. | ERG | B | Will add bid item and callout to be reset to finish grade. MAG DTL 120 TYPE B | A
15 | JBC | KH | 3 | Can Wilson verify that the survey control points are still valid? | ERG | B | Survey control points will be verified for validity | A
16 | TRACE/TOF | LR | 6 | Are bid items needed for the following: Public Notification signange, AZPDES Permitting/SWPPP, Clearing & Grubbing, Off-Duty Police Allowance, Survey Marker? Review comments and add other necessary items. | ERG | B | All bid items will be reviewed and adjusted accordingly | A
17 | JBC | AND | 6 | It appears that the item numbering is based on ADOT's standard specifications. Should ADOT or MAG be followed? | ERG | B | Correct number will be used and updated | A
18 | TRACE/TOF | LR | 6 | Typical - Consider sorting by item number. | ERG | A | Will be sorted by decending item number | A
19 | TRACE/TOF | LR | 6 | Need quantities for 2030201 and 2030507. | ERG | A | Quantities will be added | A
20 | TRACE/TOF | LR | 6 | Would 2030301 and 2030507 cover the work for 2050001 "Grading for roadway pavement"? | ERG | B | Will look into quantity to make final decision on what it covers "Grading for roadway pavement" is for subgrade preperation so it is needed to be included separate from excation and fill | D
21 | TRACE/TOF | LR | 6 | 350.01500 this doesn't match formatting of other item #'s | ERG | D | This item is not longer relevant to the revised design and will be removed | D
22 | TRACE/TOF | LR | 6 | 7040005/7040006 Doesn't match signing/markinng note 6 on sheet 23. Verify thickness to be used. | ERG | B | Correct value will be used | A
23 | TRACE/TOF | LR | 6 | 6070035 Please specify the sign post type as 2" square. | ERG | A | Will be specified | A
24 | TRACE/TOF | LR | 6 | 6080106 Are the new sign posts and foundations quantified separately?/ Is this item for remove/reinstall of a sign panel on a new post? Consider revising the item description. | ERG | A | Item description will be adjusted for clarification | A
25 | TRACE/TOF | LR | 6 | 6080025 Clarify retro-reflectivity requirements as needed. | ERG | A | Will be clarified | A
26 | TRACE/TOF | LR | 6 | What is the difference between 2020400 and 7330620? | ERG | D | 2020400 is for utility marker relocation 7330620 is for Relocating traffic signals both are required and are separate items | A
27 | TRACE/TOF | LR | 6 | 7310070 Spelling of "pole". Revise. | ERG | A | Spelling error will be fixed | A
28 | TRACE/TOF | LR | 6 | 7310820 This is only for signal pole foundations or does it cover all types of foundations? Consider revising item description. | ERG | A | Item description will be adjusted for clarification | A
29 | TRACE/TOF | LR | 6 | 7310820 Consider quantifying as an EACH item not LS. | ERG | A | Item will be changed to each to quantify correctly | A
30 | TRACE/TOF | LR | 6 | 7330620/7330630 Please give detail in specs if this cover the pole only, pole and foundation or mast arm w/ equipment? | ERG | A | Detail in specs will be given | A
31 | TRACE/TOF | LR | 6 | 7370100 What does this item over? Detail in the specs what this work involves. | ERG | B | Will look into this item | A
32 | TRACE/TOF | LR | 6 | 7378910 Is this for the signals? Consider revising to sommething like "traffic Signal Wiring & Cabling" so contractor knows what sheets to look at. | ERG | A | Item will be adjusted to be more descriptive | A
33 | TRACE/TOF | LR | 7 | Hunt Highway Typical Section 1: Typical for all typical ections - Cross-slopes shown don't match the values shown on the Cross Section Plans. | ERG | B | Will revise typicals to reflect the variety in the existing cross-slopes that are being matched, primarily in the milling sections. | A
34 | TRACE/TOF | LR | 7 | Flexible Pavement Section Detail: Reconsider tack coat between AC and AB is not needed. | ERG | B | Tack coat will be applied between AC lifts and prior to AC is placed in the milled areas. | A
35 | JBC | AE | 7 | Please confirm the asphalt binder to be used and mix including gradations and lift thicknesses for the full depth pavement section. | ERG | B | Structural section has been revised and reflected in the plans. | A
36 | JBC | AE | 7 | Please confirm if the aggragate base should conform to ADOT or MAG specifications. | ERG | B | Will look into the correct standard required | A
37 | JBC | KH | 7 | Please confirm the asphalt binder and mix for the 2" overlay pavement section. | ERG | B | Tack coat will be applied between AC lifts and prior to AC is placed in the milled areas. | A
38 | JBC | AND | 7 | Typical Section #3 - Is ABC needed for any other shoulders/slopes? | ERG | B | Revised typical section that removed the ABC in the shoulder embankment | A
39 | JBC | AND | 7 | Should crack sealing be considered after mainline milling and prior to overlay? | ERG | B | Yes, crack sealing has been added to the design plans, qtys, specs. | A
40 | TRACE/TOF | LR | 8 | Hunt Highway Typical Section 7: Travel lane doesn't match paving plans for thi station range. | ERG | D | This section no longer falls within scope of project | D
41 | TRACE/TOF | LR | 9 | Check sight distance and consider head alignment. | TWT | B | Confirmed sight distance and signal head alignment | A
42 | TRACE/TOF | LR | 9 | Check placement of signal heads along with lane alignment. | TWT | B | Checked placement of signal heads | A
43 | TRACE/TOF | LR | 9 | Review if signage for turning movements is needed. | TWT | B | Added turning movment signs | A
44 | TRACE/TOF | LR | 9 | WB left protected only? Will WB left permissive movement be allowed? | TWT | B | Evaluated and final design will reflect change | A
45 | TRACE/TOF | LR | 9 | Pull box schedule: No removal note was shown for the removal of the junction box. | TWT | B | Will verify and update | A
46 | JBC | KH | 9 | Can Wilson verify that the junction box shown just south of the existing/proposed guardrail (has construction notes #9 & #3) is part of the traffic signal equipment and is not a Zayo vault? | TWT | B | This is a Zayo Vault to be protected in place and be reset to final grade | A
47 | TRACE/TOF | LR | 10 | Station 21+41.30 is this a Type A or a Type G? | TWT | B | Will verify and update | A
48 | TRACE/TOF | LR | 10 | Station 21+40.18 How long would it take to relocate this pole? Would the intersection need to be closed or will there be temporary signals used? Consider installinga new pole and reove/salvage the old one. This would allow the new pole to be put in ervice and will minimize closure times. | TWT | B | Contractor shall provide TCP for Town approval | D
49 | TOF | LR | 11 | Typical - Recommned quantifying existing pavement removal between sawcut and existing edge of pavement. (Non-payable item since subgrade prep should cover cost). | ERG | A | Removal will be quantified (NPI, not pay item) information only | A
50 | TOF | LR | 11 | Removal note 7: Reference a standard detail | ERG | A | revised to "RESET FRAME AND COVER FOR MANHOLE (MAG DTL 422-1)" this will be new bid item # 5050202 | A
51 | TOF | LR | 11 | This intersection may need curb ramps and crosswalks in the future. Can pole placement consider those future improvements to prevent future relocation? | ERG | D | Potential for future sidewalks and sidewalk ramps were not part of the scope for this project and was not taken into consideration. | D
52 | TOF | LR | 11 | Typical - Missing roll curb construction notes. | ERG | A | Roll curb construction note will be added | A
53 | TOF | LR | 11 | Review clear zone requirements. 4" roll curb doesn't offer protection. May need to consider alternatives. | ERG | B | Clear Zone of 14' is met from travel through lane at speeds less than 40 mph | D
54 | TOF | LR | 11 | How is stormwater runoff being managed? | ERG | D | Stormwater runoff is maintaining existing historical drainage patterns, rip rap will be added to the end of the curb sections along Attaway to dissipate the concentrated flows at those locations. | D
55 | JBC | AE | 11 Through 15 | Safety Edge callouts do not match lengths listed in Construction Notes - Please Verify. | ERG | B | Check and revise quantity accordingly - will add safet edge to typicals for clarification | A
56 | TRACE/TOF | LR | 12 | Fix the hatch color (mill vs new pavement) | ERG | B | Will change shading to a hatch pattern for clarification | A
57 | TRACE/TOF | LR | 12 | Typical - shoulder linework doesn't appear to line-up with existing pavement edge. | ERG | B | Correct, the existing shoulder pavement is ~2' wide the new shoulder pavement will be 4" wide- there will be a notch of 2' at the ends of the project. | D
58 | TRACE/TOF | LR | 13 | STA 60+08.59 There's an existing culvert here that's being shown in fill, but pipe has a protect in place callout above. Review if headwall needed and confirm where runoff is being conveyed/stored. | ERG | D | The improvements at the Felix intersection have been removed from this updated project, by the Town's direction. These sheets will not be needed they are outside of the new scope | D
59 | TRACE/TOF | LR | 13 | Is this an existing channel? Will it have enough capacity with all this fill? Will the runoff still convey where it needs to with the cut/fill grading? | ERG | D | The improvements at the Felix intersection have been removed from this updated project, by the Town's direction. These sheets will not be needed they are outside of the new scope | D
60 | TRACE/TOF | LR | 13 | There's no abbreviation list included on the plans. Consider adding to minimize misinterpretation by contractor. | ERG | D | The improvements at the Felix intersection have been removed from this updated project, by the Town's direction. These sheets will not be needed they are outside of the new scope | D
61 | TRACE/TOF | LR | 14 | Does the paved shoulder have the same thickness as the road? If not, coulld it require a new full section of pavement instead of milling? | ERG | D | The improvements at the Felix intersection have been removed from this updated project, by the Town's direction. These sheets will not be needed they are outside of the new scope | D
62 | JBC | AE | 15 | Are drainage controls needed for the ends of curb? (Spillways or Riprap) | ASF | B | since the sheet flow will be concentrated at the end of the rolled curb sections on Attaway Rd, 4" thick, gravel mulch, has been added at these two locations and will be shown on the plans. ~4'W x 10'L | A
63 | JBC | AE | 15 | Please verify that the current inprovements to the SCIDD Irrigation canal will accommodate these plans. | ASF | A | Yes the current improvements to the canal accommodates this intersection design. | A
64 | JBC | AND | 16 | Callouts for PCs and PTs | ERG | A | Additional callouts will be added, included PCs and PTs for clarification. | A
65 | TRACE/TOF | LR | 21 | Does the fill slope allow for maneuverable access for SCIDD? | ASF | A | Yes SCIDD will have access, the fill slopes are flatten in this area. | A
66 | TRACE/TOF | LR | 21 | Typical - at all curb end points use a termination instead of a transition. | ERG | B | this is a 4" rolled curb that will transistion to a 24" wide flate ribbon curb. The termination curb that you are referencing is typically used for a 6" vertical curb. This is not the case for this design. MAG TYPE C transitions to MAG TYPE B. We will add additional notes for clarification. And add to specs that the 5' transitions to Type B curb are to be paid as Type B. | A
67 | TRACE/TOF | LR | 23 | Consider adding ADOT specification numbers. | ERG | A | Will Use ADOT numbers | A
68 | TRACE/TOF | LR | 23 | Everything else uses ADOT standards. Why use MAG for sign posts instead of ADOT? | ERG | A | Will change to ADOT | A
69 | TRACE/TOF | LR | 23 | (6) For permanent striping we should use thermoplastic 60mil (4") and 90mil for marking symbols. | ERG | D | Thermoplastic specification are given as a minimum. | D
70 | TRACE/TOF | LR | 23 | (8) Why wouldn't the striping plans be to scale? Consider deleting this note and reviewing the striping plans to ensure there's enough info to construct. | ERG | A | Will remove or adjust note sheets are already set to 40 scale | A
71 | TRACE/TOF | LR | 23 | (13) Very similar to Note 4. Consider combining the two. | ERG | B | Will look into best way to go about the two notes | A
72 | TRACE/TOF | LR | 23 | Consider adding notes for signage that cover: sign panel material and requirements, sign post bury depth, sign sign pangel installation height and offset from road, sign panel retro-reflective requirements, sign post clearance to existing utilities. | ERG | B | Additional notes will be added to reference generla rThis information is covered in ADOT standard specs and details for each item | D
73 | TRACE/TOF | LR | 24 | Add appropriate signage for speed change if needed. | IMD | D | Appropriate speed reduction signage exists already; noted as "relocate" on current plans. | D
74 | TRACE/TOF | LR | 24 | Consider adding sign R3-8SR to R3-20R. | ERG | A | New sign and post will be added to plans | A
75 | TRACE/TOF | LR | 24 | Consider adding R3-4 for EB and WB traffic on mast arm. | IMD | B | Signage considered optional, will not be adding at this stage | D
76 | TRACE/TOF | LR | 24 | Consider addig R10-6 ("stop here on red"). | IMD | B | Signage considered optional, will not be adding at this stage | D
77 | TRACE/TOF | LR | 24 | Typ - Add missing control notes (sta/off) and dims for new striping. Recommend showing start/end points, curve points, angle points, etc. | IMD | B | Missing control notes will be added as needed | A
78 | TRACE/TOF | LR | 25 | Consider adding W3-5 or W3-5aAZ sign (reduced speed ahead) | IMD | D | Appropriate speed reduction signage exists already; noted as "relocate" on current plans. | D
79 | TRACE/TOF | LR | 25 | Consider adding sign R3-8LS. | ERG | A | Sign will be added | A
80 | TRACE/TOF | LR | 26 | Consider adding sign R3-8LR. | ERG | D | The improvements at the Felix intersection have been removed from this updated project, by the Town's direction. These sheets will not be needed they are outside of the new scope | D
81 | TRACE/TOF | LR | 26 | Typ - Review signage against other comments on roadway plans. | ERG | D | The improvements at the Felix intersection have been removed from this updated project, by the Town's direction. These sheets will not be needed they are outside of the new scope | D
82 | TRACE/TOF | LR | 33 | "Hunt Highway & Attaway Road" - Title implies cross-section is for two roads. Could use "Hunt Highway" or "Hunt Highway @ Attaway Road". | ERG | A | Will revise title for clarification | A
83 | TRACE/TOF | LR |  | Typ - Review cross slopes. Some (-.1%) are too flat and could cause ponding on the road. | ERG | B | Cross slopes will be evaluated for proper drainage | A