## TRFC, TTC - SOSSAMAN TRK 120
Exhibit S - PIRATE Industrial Lead - 3/9/2026
TRFC, TRAFFIC CONTROL (Bid Line Item 5.01)
Sossaman Road (Track 120), PH004
| TRFC, TRAFFIC CONTROL |  |  |  |  | NOTES
| Service Item Description | QTY | UOM | Max Rate | Total Amount
| All Phases - Coordination & Permitting | 1 | LS | 0 | 0 | All Phases - agency/contractor/utility coordination, applications, obtainment of all TTC permits, haul routes, etc.
| All Phases - TTC Design & Plans | 1 | LS | 0 | 0 | All Phases - TTC layout, engineering design, drawings for all phases of construction
| All Phases - COM TTC Fees | 1 | LS | 0 | 0 | All Phases - COM TTC Fees (contractor reimbursement)
| Phase 1 - Install TTC Detour | 1 | LS | 0 | 0 | Phase 1 - install TTC detour (pavement markings, barricading, signing, flagging)
| Phase 2 - Install TTC Detour | 1 | LS | 0 | 0 | Phase 2 - install TTC detour (pavement markings, barricading, signing, flagging)
| Phase 2 - Remove Crossing Pavement & Prepare Trackbed | 67 | SY | 0 | 0 | Phase 2 - remove crossing pavement & prepare trackbed (saw cut, remove pavement, grading, place subballast)
| Phase 2 - Install 6" Dia. Underdrain | 120 | LF | 0 | 0 | Phase 2 - install 6" underdrain, south side only
| Phase 2 - Construct Crossing Pavement | 28 | SY | 0 | 0 | Phase 2 - construct pavement along track panels
| Phase 2 - Restoration | 1 | LS | 0 | 0 | Phase 2 - remove TTC and temporary pavements, restore site, open to traffic
|  |  |  | TOTAL | 0
Enter total in 1 LS for Line Item 5.01 - TRFC, TRAFFIC CONTROL
NOTE: | Quantities listed above are estimated amounts to solely demonstrate a magnitude of the item involved in
the work for the purpose of establishing a unit price for any additional work deemed necessary, in writing,
by the Railroad and establishing a basis for a monthly pay schedule. These quantities are estimates only and
are not to be relied upon by the Contractor as a material take-off for the work at hand. The Contractor is solely
responsible for determining the actual quantities involved for fully completing the project and shall not rely on the
numbers above for estimating or ordering.

## TRFC, TTC - PECOS
Exhibit S - PIRATE Industrial Lead - 3/9/2026
TRFC, TRAFFIC CONTROL (Bid Line Item 5.13)
Pecos Road, PH005 to PH012
| TRFC, TRAFFIC CONTROL |  |  |  |  | NOTES
| Service Item Description | QTY | UOM | Max Rate | Total Amount
| All Phases - Coordination & Permitting | 1 | LS | 0 | 0 | All Phases - agency/contractor/utility coordination, applications, obtainment of all TTC permits, haul routes, etc.
| All Phases - TTC Design & Plans | 1 | LS | 0 | 0 | All Phases - TTC layout, engineering design, drawings for all phases of construction
| All Phases - COM TTC Fees | 1 | LS | 0 | 0 | All Phases - COM TTC Fees (contractor reimbursement)
| Phase 1 - Install TTC | 1 | LS | 0 | 0 | Phase 1 - install TTC for temporary shoofly construction (pavement markings, barricading, signing, flagging)
| Phase 1 - Construct Temporary Shoofly | 1436 | SY | 0 | 0 | Phase 1 - construct temporary shoofly (sawcut/remove exist. pavement, grading, aggregate base course, temporary pavement)
| Phase 1 - Temporary Shoring | 1 | LS | 0 | 0 | Phase 1 - temporary shoring system (engineering design, installation, maintenance, removal)
| Phase 1 - Install TTC | 1 | LS | 0 | 0 | Phase 1 - install TTC for diverting traffic to temporary shoofly (pavement markings, barricading, signing, flagging)
| Phase 2 - Temporary Paving | 579 | SY | 0 | 0 | Phase 2 - construct temporary pavement necessary for Phase 2 (grading, aggregate base course, asphalt)
| Phase 2 - Install TTC | 1 | LS | 0 | 0 | Phase 2 - install TTC for diverting traffic to Phase 1 improvements (pavement markings, barricading, signing, flagging)
| Phase 2 - Temporary Shoring | 1 | LS | 0 | 0 | Phase 2 - temporary shoring system (engineering design, installation, maintenance, removal)
| Phase 2 - Remove Shoofly Pavement | 1418 | SY | 0 | 0 | Phase 2 - remove shoofly pavement, finish grading
| Phase 3 - Install TTC | 1 | LS | 0 | 0 | Phase 3 - install TTC for access drive closure
| Phase 3 - Remove Temporary Pavement | 191 | SY | 0 | 0 | Phase 3 - remove temporary access drive pavement from Phase 2
| Phase 4 - Install TTC (Full-Closure, Detour) | 1 | LS | 0 | 0 | Phase 4 - install TTC detour (pavement markings, barricading, signing, flagging)
| Phase 4 - Remove Crossing Pavement & Prepare Trackbed | 110 | SY | 0 | 0 | Phase 4 - remove crossing pavement & prepare trackbed (saw cut, remove pavement, grading, place subballast)
| Phase 4 - Remove Temporary Pavement | 406 | SY | 0 | 0 | Phase 4 - remove temporary pavement from Phase 3
| Phase 4 - Install 6" Dia. Underdrain | 340 | LF | 0 | 0 | Phase 4 - install 6" underdrain, both sides (cap on south, outlet to north ditches)
| Phase 4 - Construct Crossing Pavement | 32 | SY | 0 | 0 | Phase 4 - construct pavement along track panels
| Phase 4 - Restoration | 1 | LS | 0 | 0 | Phase 4 - remove TTC and temporary pavements, restore site, open to traffic
|  |  |  | TOTAL | 0
Enter total in 1 LS for Line Item 5.13 - TRFC, TRAFFIC CONTROL
NOTE: | Quantities listed above are estimated amounts to solely demonstrate a magnitude of the item involved in
the work for the purpose of establishing a unit price for any additional work deemed necessary, in writing,
by the Railroad and establishing a basis for a monthly pay schedule. These quantities are estimates only and
are not to be relied upon by the Contractor as a material take-off for the work at hand. The Contractor is solely
responsible for determining the actual quantities involved for fully completing the project and shall not rely on the
numbers above for estimating or ordering.

## TRFC, TTC - SOSSAMAN
Exhibit S - PIRATE Industrial Lead - 3/9/2026
TRFC, TRAFFIC CONTROL (Bid Line Item 5.45)
Sossaman Road, PH013 to PH018
| TRFC, TRAFFIC CONTROL |  |  |  |  | NOTES
| Service Item Description | QTY | UOM | Max Rate | Total Amount
| All Phases - Coordination & Permitting | 1 | LS | 0 | 0 | All Phases - agency/contractor/utility coordination, applications, obtainment of all TTC permits, haul routes, etc.
| All Phases - TTC Design & Plans | 1 | LS | 0 | 0 | All Phases - TTC layout, engineering design, drawings for all phases of construction
| All Phases - COM TTC Fees | 1 | LS | 0 | 0 | All Phases - COM TTC Fees (contractor reimbursement)
| Phase 1A - Install TTC | 1 | LS | 0 | 0 | Phase 1A - install TTC for shoofly construction (pavement markings, barricading, signing, flagging)
| Phase 1A - Construct Temporary Shoofly | 1847 | SY | 0 | 0 | Phase 1A - construct temporary shoofly (grading, aggregate base course, temporary pavement)
| Phase 1A - Temporary Shoring | 1 | LS | 0 | 0 | Phase 1A - temporary shoring system (engineering design, installation, maintenance, removal)
| Phase 1B - Install TTC | 1 | LS | 0 | 0 | Phase 1B - install TTC for access drive closure
| Phase 2 - Temporary Paving | 151 | SY | 0 | 0 | Phase 2 - construct temporary pavement necessary for Phase 3 (grading, aggregate base course, asphalt)
| Phase 2 - Install TTC | 1 | LS | 0 | 0 | Phase 2 - install TTC for diverting traffic to Phase 1A & 1B pavement construction (pavement markings, barricading, signing, flagging)
| Phase 2 - Temporary Shoring | 1 | LS | 0 | 0 | Phase 2 - temporary shoring system (engineering design, installation, maintenance, removal)
| Phase 2 - Remove Shoofly Pavement | 1847 | SY | 0 | 0 | Phase 2 - remove shoofly pavement, finish grading
| Phase 3 - Install TTC (Full-Closure, Detour) | 1 | LS | 0 | 0 | Phase 3 - install TTC detour (pavement markings, barricading, signing, flagging)
| Phase 3 - Remove Temporary Pavement | 151 | SY | 0 | 0 | Phase 3 - remove temporary pavement from Phase 2
| Phase 3 - Remove Crossing Pavement & Prepare Trackbed | 155 | SY | 0 | 0 | Phase 3 - remove crossing pavement & prepare trackbed (saw cut, remove pavement, grading, place subballast)
| Phase 3 - Install 6" Dia. Underdrain | 465 | LF | 0 | 0 | Phase 3 - install 6" underdrain, both sides (cap on east, outlet to west ditches)
| Phase 3 - Construct Crossing Pavement | 45 | SY | 0 | 0 | Phase 3 - construct pavement along track panels
| Phase 3 - Restoration | 1 | LS | 0 | 0 | Phase 3 - remove TTC and temporary pavements, restore site, open to traffic
|  |  |  | TOTAL | 0
Enter total in 1 LS for Line Item 5.45 - TRFC, TRAFFIC CONTROL
NOTE: | Quantities listed above are estimated amounts to solely demonstrate a magnitude of the item involved in
the work for the purpose of establishing a unit price for any additional work deemed necessary, in writing,
by the Railroad and establishing a basis for a monthly pay schedule. These quantities are estimates only and
are not to be relied upon by the Contractor as a material take-off for the work at hand. The Contractor is solely
responsible for determining the actual quantities involved for fully completing the project and shall not rely on the
numbers above for estimating or ordering.

## TRFC, TTC - ELLSWORTH
Exhibit S - PIRATE Industrial Lead - 3/9/2026
TRFC, TRAFFIC CONTROL (Bid Line Item 6.01)
Ellsworth Road, PH019 to PH027
| TRFC, TRAFFIC CONTROL |  |  |  |  | NOTES
| Service Item Description | QTY | UOM | Max Rate | Total Amount
| All Phases - Coordination & Permitting | 1 | LS | 0 | 0 | All Phases - agency/contractor/utility coordination, applications, obtainment of all TTC permits, haul routes, etc.
| All Phases - TTC Design & Plans | 1 | LS | 0 | 0 | All Phases - TTC layout, engineering design, drawings for all phases of construction
| All Phases - COM TTC Fees | 1 | LS | 0 | 0 | All Phases - COM TTC Fees (contractor reimbursement)
| Phase 1 - Install TTC (Shoofly Pavement) | 1 | LS | 0 | 0 | Phase 1 - install TTC for shoofly construction (pavement markings, barricading, signing, flagging)
| Phase 1 - Construct Temporary Shoofly | 1349 | SY | 0 | 0 | Phase 1 - construct temporary shoofly (remove sidewalk, remove curb, remove access drives, grading, aggregate base course, temporary pavement)
| Phase 1 - Install TTC (Temporary Median Pavement) | 1 | LS | 0 | 0 | Phase 1 - install TTC for temporary median pavement (pavement markings, barricading, signing, flagging)
| Phase 1 - Construct Temporary Median Pavement | 2044 | SY | 0 | 0 | Phase 1 - construct temporary median pavement (remove curb, grading, adj. fiber pull boxes, aggregate base course, temporary pavement)
| Phase 1 - Install TTC | 1 | LS | 0 | 0 | Phase 1 - install TTC for diverting traffic to temporary shoofly and median crossovers (pavement markings, barricading, signing, flagging)
| Phase 2 - Install TTC | 1 | LS | 0 | 0 | Phase 2 - install TTC for diverting NB traffic to Phase 1 improvements (pavement markings, barricading, signing, flagging)
| Phase 2 - Remove Temporary Median Pavement | 2044 | SY | 0 | 0 | Phase 2 - remove median pavement (adj. fiber pull boxes, reconstruct median curb, backfill median, landscaping)
| Phase 3 - Install TTC | 1 | LS | 0 | 0 | Phase 3 - install TTC to divert SB traffic to Phase 2 improvements (pavement markings, barricading, signing, flagging)
| Phase 3 - Remove Temporary Shoofly Pavement | 1349 | SY | 0 | 0 | Phase 3 - remove temporary shoofly (reconstruct sidewalk, reconstruct access drives, culvert)
| Phase 4 - Install TTC (Full-Closure, Detour) | 1 | LS | 0 | 0 | Phase 4 - install TTC detour (pavement markings, barricading, signing, flagging)
| Phase 4 - Remove Crossing Pavement & Prepare Trackbed | 148 | SY | 0 | 0 | Phase 4 - remove crossing pavement & prepare trackbed (saw cut, remove pavement, grading, place subballast)
| Phase 4 - Install 6" Dia. Underdrain | 280 | LF | 0 | 0 | Phase 4 - install 6" underdrain, both sides (cap on west, outlet to Ellsworth Channel)
| Phase 4 - Construct Crossing Pavement | 45 | SY | 0 | 0 | Phase 4 - construct pavement along track panels
| Phase 4 - Restoration | 1 | LS | 0 | 0 | Phase 4 - remove TTC and temporary pavements, restore site, open to traffic
|  |  |  | TOTAL | 0
Enter total in 1 LS for Line Item 6.01 - TRFC, TRAFFIC CONTROL
NOTE: | Quantities listed above are estimated amounts to solely demonstrate a magnitude of the item involved in
the work for the purpose of establishing a unit price for any additional work deemed necessary, in writing,
by the Railroad and establishing a basis for a monthly pay schedule. These quantities are estimates only and
are not to be relied upon by the Contractor as a material take-off for the work at hand. The Contractor is solely
responsible for determining the actual quantities involved for fully completing the project and shall not rely on the
numbers above for estimating or ordering.

## TRFC, TTC - CRISMON
Exhibit S - PIRATE Industrial Lead - 3/9/2026
TRFC, TRAFFIC CONTROL (Bid Line Item 6.26)
Crismon Road, PH028
| TRFC, TRAFFIC CONTROL |  |  |  |  | NOTES
| Service Item Description | QTY | UOM | Max Rate | Total Amount
| All Phases - Coordination & Permitting | 1 | LS | 0 | 0 | All Phases - agency/contractor/utility coordination, applications, obtainment of all TTC permits, haul routes, etc.
| All Phases - TTC Design & Plans | 1 | LS | 0 | 0 | All Phases - TTC layout, engineering design, drawings for all phases of construction
| All Phases - COM TTC Fees | 1 | LS | 0 | 0 | All Phases - COM TTC Fees (contractor reimbursement)
| Phase 1 - Install TTC (Full-Closure, Detour) | 1 | LS | 0 | 0 | Phase 1 - install TTC detour (pavement markings, barricading, signing, flagging)
| Phase 2 - Install TTC (Full-Closure, Detour) | 1 | LS | 0 | 0 | Phase 2 - install TTC detour (pavement markings, barricading, signing, flagging)
| Phase 2 - Remove Crossing Pavement & Prepare Trackbed | 110 | SY | 0 | 0 | Phase 2 - remove crossing pavement & prepare trackbed (saw cut, remove pavement, grading, place subballast)
| Phase 2 - Install 6" Dia. Underdrain | 250 | LF | 0 | 0 | Phase 2 - install 6" underdrain, both sides
| Phase 2 - Construct Crossing Pavement | 34 | SY | 0 | 0 | Phase 2 - construct pavement along track panels
| Phase 2 - Restoration | 1 | LS | 0 | 0 | Phase 2 - remove TTC and temporary pavements, restore site, open to traffic
|  |  |  | TOTAL | 0
Enter total in 1 LS for Line Item 6.26 - TRFC, TRAFFIC CONTROL
NOTE: | Quantities listed above are estimated amounts to solely demonstrate a magnitude of the item involved in
the work for the purpose of establishing a unit price for any additional work deemed necessary, in writing,
by the Railroad and establishing a basis for a monthly pay schedule. These quantities are estimates only and
are not to be relied upon by the Contractor as a material take-off for the work at hand. The Contractor is solely
responsible for determining the actual quantities involved for fully completing the project and shall not rely on the
numbers above for estimating or ordering.

## TRFC, TTC - SIGNAL BUTTE
Exhibit S - PIRATE Industrial Lead - 3/9/2026
TRFC, TRAFFIC CONTROL (Bid Line Item 6.43)
Signal Butte Road, PH029
| TRFC, TRAFFIC CONTROL |  |  |  |  | NOTES
| Service Item Description | QTY | UOM | Max Rate | Total Amount
| All Phases - Coordination & Permitting | 1 | LS | 0 | 0 | All Phases - agency/contractor/utility coordination, applications, obtainment of all TTC permits, haul routes, etc.
| All Phases - TTC Design & Plans | 1 | LS | 0 | 0 | All Phases - TTC layout, engineering design, drawings for all phases of construction
| All Phases - COM TTC Fees | 1 | LS | 0 | 0 | All Phases - COM TTC Fees (contractor reimbursement)
| Phase 1 - Install TTC (Full-Closure, Detour) | 1 | LS | 0 | 0 | Phase 1 - install TTC detour (pavement markings, barricading, signing, flagging)
| Phase 1 - Install TTC (Full-Closure, Detour) | 1 | LS | 0 | 0 | Phase 2 - install TTC detour (pavement markings, barricading, signing, flagging)
| Phase 2 - Remove Crossing Pavement & Prepare Trackbed | 51 | SY | 0 | 0 | Phase 2 - remove crossing pavement & prepare trackbed (saw cut, remove pavement, grading, place subballast)
| Phase 2 - Install 6" Dia. Underdrain | 90 | LF | 0 | 0 | Phase 2 - install 6" underdrain, south side only
| Phase 2 - Construct Crossing Pavement | 15 | SY | 0 | 0 | Phase 2 - construct pavement along track panels
| Phase 2 - Restoration | 1 | LS | 0 | 0 | Phase 2 - remove TTC and temporary pavements, restore site, open to traffic
|  |  |  | TOTAL | 0
Enter total in 1 LS for Line Item 6.43 - TRFC, TRAFFIC CONTROL
NOTE: | Quantities listed above are estimated amounts to solely demonstrate a magnitude of the item involved in
the work for the purpose of establishing a unit price for any additional work deemed necessary, in writing,
by the Railroad and establishing a basis for a monthly pay schedule. These quantities are estimates only and
are not to be relied upon by the Contractor as a material take-off for the work at hand. The Contractor is solely
responsible for determining the actual quantities involved for fully completing the project and shall not rely on the
numbers above for estimating or ordering.

## TRFC, TTC - PECOS (EAST)
Exhibit S - PIRATE Industrial Lead - 3/9/2026
TRFC, TRAFFIC CONTROL (Bid Line Item 6.58)
Pecos Road (East) Half-Street Improvements, R042
| TRFC, TRAFFIC CONTROL |  |  |  |  | NOTES
| Service Item Description | QTY | UOM | Max Rate | Total Amount
| All Phases - Coordination & Permitting | 1 | LS | 0 | 0 | All Phases - agency/contractor/utility coordination, applications, obtainment of all TTC permits, haul routes, etc.
| All Phases - TTC Design & Plans | 1 | LS | 0 | 0 | All Phases - TTC layout, engineering design, drawings for all phases of construction
| All Phases - COM TTC Fees | 1 | LS | 0 | 0 | All Phases - COM TTC Fees (contractor reimbursement)
| Phase 1 - Install TTC (Lane Shift) | 1 | LS | 0 | 0 | Phase 1 - TTC for installation of temporary pavement for lane shift (pavement markings, barricading, signing, flagging)
| Phase 1 - Temporary Paving | 320 | SY | 0 | 0 | Phase 1 - construct temporary pavement necessary for lane shift (grading, aggregate base course, asphalt)
| Phase 2 - Install TTC | 1 | LS | 0 | 0 | Phase 2 - TTC to divert traffic to lane shift
| Phase 2 - Restoration | 1 | LS | 0 | 0 | Phase 2 - remove TTC and temporary pavements, restore site, open to traffic
|  |  |  | TOTAL | 0
Enter total in 1 LS for Line Item 6.58 - TRFC, TRAFFIC CONTROL
NOTE: | Quantities listed above are estimated amounts to solely demonstrate a magnitude of the item involved in
the work for the purpose of establishing a unit price for any additional work deemed necessary, in writing,
by the Railroad and establishing a basis for a monthly pay schedule. These quantities are estimates only and
are not to be relied upon by the Contractor as a material take-off for the work at hand. The Contractor is solely
responsible for determining the actual quantities involved for fully completing the project and shall not rely on the
numbers above for estimating or ordering.

## UTIL, ELECTRICAL
Exhibit S - PIRATE Industrial Lead - 3/9/2026
UTIL, ELECTRICAL, COMPLETE (Bid Line Item 10.01)
E001 to E501
| UTIL, ELECTRICAL, COMPLETE |  |  |  |  | NOTES
| Service Item Description | QTY | UOM | Max Rate | Total Amount
Pecos Road
| XHHW-2 STRANDED #12 | 1800 | LF | 0 | 0
| XHHW-2 STRANDED #10 | 3000 | LF | 0 | 0
| XHHW-2 STRANDED #8 | 0 | LF | 0 | 0
| XHHW-2 STRANDED #6 | 600 | LF | 0 | 0
| XHHW-2 STRANDED #4 | 200 | LF | 0 | 0
| XHHW-2 STRANDED #2 | 0 | LF | 0 | 0
| XHHW-2 STRANDED #1 | 1700 | LF | 0 | 0
| XHHW-2 STRANDED #1/0 | 0 | LF | 0 | 0
| XHHW-2 STRANDED #2/0 | 0 | LF | 0 | 0
| XHHW-2 STRANDED #3/0 | 120 | LF | 0 | 0
| XHHW-2 STRANDED #4/0 | 0 | LF | 0 | 0
Sossaman Road
| XHHW-2 STRANDED #12 | 1800 | LF | 0 | 0
| XHHW-2 STRANDED #10 | 3000 | LF | 0 | 0
| #4 Triplex, OH conductor | 400 | LF | 0 | 0
| #6 Triplex, OH conductor | 1000 | LF | 0 | 0
| 3/4" Conduit - RGS | 360 | LF | 0 | 0 | Any conduit installation at 3' below and above. Includes all fittings, elbows, weather-tight connectors
| 3/4" Conduit - PVC | 900 | LF | 0 | 0
| 1" Conduit - RGS only | 300 | LF | 0 | 0 | Any conduit installation at 3' below and above. Includes all fittings, elbows, weather-tight connectors
| 1" Conduit - PVC | 1700 | LF | 0 | 0
| 1-1/4" Conduit - RGS only | 20 | LF | 0 | 0 | Any conduit installation at 3' below and above. Includes all fittings, elbows, weather-tight connectors
| 2" Conduit - RGS | 500 | LF | 0 | 0 | Any conduit installation at 3' below and above. Includes all fittings, elbows, weather-tight connectors
| 2" Conduit - PVC | 400 | LF | 0 | 0 | Includes all fittings, elbows, weather-tight connectors
| 2-1/2" Conduit - PVC | 660 | LF | 0 | 0 | Includes all fittings, elbows, weather-tight connectors
| 3" Conduit - RGS | 400 | LF | 0 | 0 | Any conduit installation at 3' below and above. Includes all fittings, elbows, weather-tight connectors
| 3" Conduit - PVC | 18210 | LF | 0 | 0 | Includes all fittings, elbows, weather-tight connectors
| Wireway, NEMA 3R, at rack | 3 | EA | 0 | 0
| Junction boxes 8"x8"x4" NEMA 3R | 13 | EA | 0 | 0
| Meter socket, 240V, 200A | 1 | EA | 0 | 0
| Meter socket, 240V, 100A | 10 | EA | 0 | 0 | meets all local utility requirements
| Disconnect, heavy duty, service-rated, 240V, 200A | 1 | EA | 0 | 0 | With fuses
| Disconnect, heavy duty, service-rated, 240V, 100A | 10 | EA | 0 | 0 | With fuses
| Disconnect, heavy duty, 240V, 200A | 1 | EA | 0 | 0 | With fuses
| Disconnect, heavy duty, 240V, 100A | 6 | EA | 0 | 0 | With fuses
| Disconnect, heavy duty, 240V, 30A | 7 | EA | 0 | 0 | With fuses
| Electrical devices, 120V | 0 | EA | 0 | 0
| Electrical devices, 240V | 0 | EA | 0 | 0
| Wood Pole, Secondary assembly - 45', class 3 | 19 | EA | 0 | 0 | Include pole, hardware
| Guying | 7 | EA | 0 | 0
| Pole grounding assemblies | 19 | EA | 0 | 0 | Includes bare #6 conductor, ground rod, and connections
| Aerial marker balls | 3 | EA | 0 | 0
| Trenching and Backfill for direct bury conduits | 1500 | LF | 0 | 0 | Conduit not included
| Trenching/racking for utility conduits/concrete encasement | 6070 | LF | 0 | 0 | Encase to provide 3" cover on all sides of conduits; includes spacers
| Horizontal Boring and Set Up, include steel casing | 1100 | LF | 0 | 0 | Repair surface to match surrounding
| Equipment Rack w/ Foundation - Large | 3 | EA | 0 | 0 | Supports 3 or more devices (disconnects, meters, etc) - includes RGS supports
| Equipment Rack w/ Foundation - Small | 12 | EA | 0 | 0 | Supports <3 devices (disconnects, meters, etc.) - includes RGS supports
| Concrete filled pipe bollards | 18 | EA | 0 | 0
| Roadway light | 11 | EA | 0 | 0 | Include luminaire, options, & mounting bracket
Common | Conduct and Submit Findings for Arc Flash Analysis - Complete | 1 | LS | 0 | 0 | Refer to Spec Section 26 99 00 for contractor responsibilities
| Utility coordination (site meetings, inspections, etc.) | 1 | LS | 0 | 0 | For all service drop locations
| Temporary Traffic Control | 1 | LS | 0 | 0
| One Year Maintenance Contract | 1 | LS | 0 | 0
ME1
E201 | Meter socket, 240V, 100A | 1 | EA | 0 | 0 | Meets all local utility requirements
| Disconnect, heavy duty, service-rated, 240V, 100A | 1 | EA | 0 | 0 | With fuses
| Disconnect, heavy duty, 240V, 100A | 1 | EA | 0 | 0 | With fuses
| Junction boxes 8"x8"x4" NEMA 3R | 1 | EA | 0 | 0
| 2" Conduit - PVC | 90 | LF | 0 | 0 | Includes all fittings, elbows, weather-tight connectors
| 2" Conduit - RGS | 10 | LF | 0 | 0 | Any conduit installation at 3' below and above. Includes all fittings, elbows, weather-tight connectors
| 2-1/2" Conduit - PVC | 150 | LF | 0 | 0 | Includes all fittings, elbows, weather-tight connectors
| XHHW-2 STRANDED #1 | 100 | LF | 0 | 0
| Concrete filled pipe bollards | 6 | EA | 0 | 0
| Equipment Rack w/ Foundation - Small | 2 | EA | 0 | 0 | Supports <3 devices (disconnects, meters, etc.) - includes RGS supports
| Horizontal Boring and Set Up, include steel casing | 240 | LF | 0 | 0 | Repair surface to match surrounding
ME2
E202 | Meter socket, 240V, 100A | 1 | EA | 0 | 0 | Meets all local utility requirements
| Disconnect, heavy duty, service-rated, 240V, 100A | 1 | EA | 0 | 0 | With fuses
| Disconnect, heavy duty, 240V, 70A | 1 | EA | 0 | 0 | With fuses
| Disconnect, heavy duty, 240V, 30A | 1 | EA | 0 | 0 | With fuses
| Junction boxes 8"x8"x4" NEMA 3R | 1 | EA | 0 | 0
| Wood Pole, Secondary assembly - 45', class 3 | 4 | EA | 0 | 0 | Include pole, hardware
| Guying | 4 | EA | 0 | 0
| Pole grounding assemblies | 4 | EA | 0 | 0 | Includes bare #6 conductor, ground rod, and connections
| Aerial marker balls | 1 | EA | 0 | 0
| Roadway light | 2 | EA | 0 | 0 | Include luminaire, options, & mounting bracket
| 3/4" Conduit - RGS | 60 | LF | 0 | 0
| 1-1/4" Conduit - RGS only | 30 | LF | 0 | 0 | Any conduit installation at 3' below and above. Includes all fittings, elbows, weather-tight connectors
| 2" Conduit - RGS | 35 | LF | 0 | 0 | Any conduit installation at 3' below and above. Includes all fittings, elbows, weather-tight connectors
| XHHW-2 STRANDED #10 | 35 | LF | 0 | 0
| XHHW-2 STRANDED #8 | 35 | LF | 0 | 0
| XHHW-2 STRANDED #4 | 35 | LF | 0 | 0
| XHHW-2 STRANDED #1 | 25 | LF | 0 | 0
| #4 Triplex, OH conductor | 430 | LF | 0 | 0
| #6 Triplex, OH conductor | 326 | LF | 0 | 0
| Concrete filled pipe bollards | 4 | EA | 0 | 0
| Equipment Rack w/ Foundation - Small | 2 | EA | 0 | 0 | Supports <3 devices (disconnects, meters, etc.) - includes RGS supports
ME3
E203 | Meter socket, 240V, 100A | 1 | EA | 0 | 0 | Meets all local utility requirements
| Disconnect, heavy duty, service-rated, 240V, 100A | 1 | EA | 0 | 0 | With fuses
| Disconnect, heavy duty, 240V, 100A | 1 | EA | 0 | 0 | With fuses
| Junction boxes 8"x8"x4" NEMA 3R | 1 | EA | 0 | 0
| Wood Pole, Secondary assembly - 45', class 3 | 1 | EA | 0 | 0 | Include pole, hardware
| Guying | 1 | EA | 0 | 0
| Pole grounding assemblies | 1 | EA | 0 | 0 | Includes bare #6 conductor, ground rod, and connections
| 2" Conduit - RGS | 40 | LF | 0 | 0 | Any conduit installation at 3' below and above. Includes all fittings, elbows, weather-tight connectors
| 2" Conduit - PVC | 105 | LF | 0 | 0 | Includes all fittings, elbows, weather-tight connectors
| XHHW-2 STRANDED #1 | 110 | LF | 0 | 0
| Concrete filled pipe bollards | 4 | EA | 0 | 0
| Equipment Rack w/ Foundation - Small | 2 | EA | 0 | 0 | Supports <3 devices (disconnects, meters, etc.) - includes RGS supports
| Horizontal Boring and Set Up, include steel casing | 105 | LF | 0 | 0 | Repair surface to match surrounding
ME4
E205 | Meter socket, 240V, 100A | 1 | EA | 0 | 0 | Meets all local utility requirements
| Disconnect, heavy duty, service-rated, 240V, 100A | 1 | EA | 0 | 0 | With fuses
| Wireway, NEMA 3R, at rack | 1 | EA | 0 | 0
| Disconnect, heavy duty, 240V, 70A | 1 | EA | 0 | 0 | With fuses
| Disconnect, heavy duty, 240V, 30A | 1 | EA | 0 | 0 | With fuses
| Junction boxes 8"x8"x4" NEMA 3R | 1 | EA | 0 | 0
| Wood Pole, Secondary assembly - 45', class 3 | 1 | EA | 0 | 0 | Include pole, hardware
| Guying | 1 | EA | 0 | 0
| Pole grounding assemblies | 1 | EA | 0 | 0 | Includes bare #6 conductor, ground rod, and connections
| 3/4" Conduit - PVC | 175 | LF | 0 | 0
| 1-1/4" Conduit - RGS | 20 | LF | 0 | 0 | Any conduit installation at 3' below and above. Includes all fittings, elbows, weather-tight connectors
| 2" Conduit - RGS | 40 | LF | 0 | 0 | Any conduit installation at 3' below and above. Includes all fittings, elbows, weather-tight connectors
| 2-1/2" Conduit - PVC | 60 | LF | 0 | 0 | Includes all fittings, elbows, weather-tight connectors
| XHHW-2 STRANDED #10 | 175 | LF | 0 | 0
| XHHW-2 STRANDED #8 | 15 | LF | 0 | 0
| XHHW-2 STRANDED #4 | 15 | LF | 0 | 0
| XHHW-2 STRANDED #1 | 20 | LF | 0 | 0
| Concrete filled pipe bollards | 2 | EA | 0 | 0
| Equipment Rack w/ Foundation - Large | 1 | EA | 0 | 0 | Supports 3 or more devices (disconnects, meters, etc) - includes RGS supports
| Trenching and Backfill for direct bury conduits | 222 | LF | 0 | 0 | Conduit not included
ME5
E206-E210 | Meter socket, 240V, 320A | 1 | EA | 0 | 0 | Meets all local utility requirements
| Disconnect, heavy duty, service-rated, 240V, 300A | 1 | EA | 0 | 0 | With fuses
| Disconnect, heavy duty, service-rated, 480V, 125A | 1 | EA | 0 | 0 | With fuses
| Disconnect, heavy duty, 240V, 250A | 1 | EA | 0 | 0 | With fuses
| Disconnect, heavy duty, 240V, 70A | 1 | EA | 0 | 0 | With fuses
| Disconnect, heavy duty, 480V, 100A | 1 | EA | 0 | 0 | With fuses
| Disconnect, heavy duty, 480V, 30A | 2 | EA | 0 | 0 | With fuses
| Transformer 120/240-480V 50 KVA | 1 | EA | 0 | 0 | Step up transformer
| Disconnect, heavy duty, 480V, 125A | 1 | EA | 0 | 0 | With fuses
| Wireway, NEMA 3R, at rack | 2 | EA | 0 | 0
| Junction boxes 8"x8"x4" NEMA 3R | 4 | EA | 0 | 0
| Junction boxes 12"x12"x4" NEMA 3R | 5 | EA | 0 | 0
| Wood Pole, Secondary assembly - 45', class 3 | 4 | EA | 0 | 0 | Include pole, hardware
| Guying | 4 | EA | 0 | 0
| Pole grounding assemblies | 4 | EA | 0 | 0 | Includes bare #6 conductor, ground rod, and connections
| Roadway light | 4 | EA | 0 | 0 | Include luminaire, options, & mounting bracket
| 1-1/4" Conduit - PVC | 3922 | LF | 0 | 0 | Any conduit installation at 3' below and above. Includes all fittings, elbows, weather-tight connectors
| 3" Conduit - PVC | 3413 | LF | 0 | 0 | Includes all fittings, elbows, weather-tight connectors
| XHHW-2 STRANDED #6 | 3922 | LF | 0 | 0
| XHHW-2 STRANDED #300 | 3258 | LF | 0 | 0
| Concrete filled pipe bollards | 10 | EA | 0 | 0
| Equipment Rack w/ Foundation - Large | 2 | EA | 0 | 0 | Supports 3 or more devices (disconnects, meters, etc) - includes RGS supports
| Trenching and Backfill for direct bury conduits | 5707 | LF | 0 | 0 | Conduit not included
ME8
E211 | Meter socket, 240V, 100A | 1 | EA | 0 | 0 | Meets all local utility requirements
| Disconnect, heavy duty, service-rated, 240V, 100A | 1 | EA | 0 | 0 | With fuses
| Junction boxes 8"x8"x4" NEMA 3R | 1 | EA | 0 | 0
| 2-1/2" Conduit - PVC | 230 | LF | 0 | 0 | Includes all fittings, elbows, weather-tight connectors
| 2" Conduit - RGS | 15 | LF | 0 | 0 | Includes all fittings, elbows, weather-tight connectors
| XHHW-2 STRANDED #1 | 25 | LF | 0 | 0
| Concrete filled pipe bollards | 2 | EA | 0 | 0
| Equipment Rack w/ Foundation - Small | 1 | EA | 0 | 0 | Supports <3 devices (disconnects, meters, etc.) - includes RGS supports
| Horizontal Boring and Set Up, include steel casing | 190 | LF | 0 | 0 | Repair surface to match surrounding
ME9
E212 | Meter socket, 240V, 100A | 1 | EA | 0 | 0 | Meets all local utility requirements
| Disconnect, heavy duty, service-rated, 240V, 100A | 1 | EA | 0 | 0 | With fuses
| Wood Pole, Secondary assembly - 45', class 3 | 1 | EA | 0 | 0 | Include pole, hardware
| Guying | 1 | EA | 0 | 0
| Pole grounding assemblies | 1 | EA | 0 | 0 | Includes bare #6 conductor, ground rod, and connections
| Junction boxes 8"x8"x4" NEMA 3R | 1 | EA | 0 | 0
| 2" Conduit - RGS | 40 | LF | 0 | 0 | Includes all fittings, elbows, weather-tight connectors
| XHHW-2 STRANDED #1 | 45 | LF | 0 | 0
| Concrete filled pipe bollards | 2 | EA | 0 | 0
| Equipment Rack w/ Foundation - Small | 1 | EA | 0 | 0 | Supports <3 devices (disconnects, meters, etc.) - includes RGS supports
ME10
E213 | Meter socket, 240V, 100A | 1 | EA | 0 | 0 | Meets all local utility requirements
| Disconnect, heavy duty, service-rated, 240V, 100A | 1 | EA | 0 | 0 | With fuses
| Junction boxes 8"x8"x4" NEMA 3R | 1 | EA | 0 | 0
| 2-1/2" Conduit - PVC | 150 | LF | 0 | 0 | Includes all fittings, elbows, weather-tight connectors
| 2" Conduit - PVC | 15 | LF | 0 | 0 | Includes all fittings, elbows, weather-tight connectors
| XHHW-2 STRANDED #1 | 25 | LF | 0 | 0
| Concrete filled pipe bollards | 2 | EA | 0 | 0
| Equipment Rack w/ Foundation - Small | 1 | EA | 0 | 0 | Supports <3 devices (disconnects, meters, etc.) - includes RGS supports
| Horizontal Boring and Set Up, include steel casing | 150 | LF | 0 | 0 | Repair surface to match surrounding
|  |  |  | TOTAL | 0
Enter total in 1 LS for Line Item 10.01 - UTIL, ELECTRICAL, COMPLETE
NOTE: | Quantities listed above are estimated amounts to solely demonstrate a magnitude of the item involved in
the work for the purpose of establishing a unit price for any additional work deemed necessary, in writing,
by the Railroad and establishing a basis for a monthly pay schedule. These quantities are estimates only and
are not to be relied upon by the Contractor as a material take-off for the work at hand. The Contractor is solely
responsible for determining the actual quantities involved for fully completing the project and shall not rely on the
numbers above for estimating or ordering.
Quantity-206
1 | -Meter Socket, 240V, 320A - ME5
1 | -Disconnect, heavy Duty, Service rated, 240V, 300A - MSW5
1 | -Disconnect, heavy Duty, 240V, 70A - SW5A
1 | -Disconnect, heavy Duty, 240V, 250A - SW5B
1 | -Transformer 50 KVA - T1
1 | -Disconnect, heavy Duty, 480V, 125A - SW5C
1 | -(1) Wire Way
1 | -(1)Junction Box 1 - 8"x8"
155 | -(155') 3"C
1890 | -(945+945=1890') 2-#300, 1-#2 G, 3"C
Quantity-207
1 | -Disconnect, heavy Duty, Service rated, 480V, 125A - MSW6
1 | -Disconnect, heavy Duty, 480V, 100A - SW6A
1 | -Disconnect, heavy Duty, 480V, 30A - SW6B
1 | -(1) Wire Way
3 | -(3)Junction Box 1 - 8"x8"
2 | -(2)Wood Pole, Secondary Assembly-45', Class 3
2 | -(2) L1 Lights
732 | -(187+143+402=732') 2-#6, #6G, 1 1/4"C
1368 | -(684+684=1368') 2-#300, 1-#2 G, 3"C
Quantity-208
2 | -(2)Junction Box 2 - 12"x12"
1392 | -(434+870+88=1392') 2-#6, #6G, 1 1/4"C
Quantity-209
1 | -(1)Junction Box 2 - 12"x12"
1402 | -(783+619=1402') 2-#6, #6G, 1 1/4"C
Quantity-210
1 | -(1) Junction Box 1- 8"x8"
1 | -SW7 - Disconnect, heavy Duty, 480V, 30A
2 | -(2)Wood Pole, Secondary Assembly-45', Class 3
2 | -(2) L1 light
396 | -(237+159=396') 2-#6, #6G, 1 1/4"C